# Meeting Notes – Q2 Planning

Date: April 18, 2026

Time: 10:00 – 11:30 AM (ICT)

Location: Conference Room B / Microsoft Teams

Facilitator: Kanokporn Wattanasuk

Attendees: Tanawat Boonlert, Siriphon Chaiyaporn, Rattana Promchai, Apinya Soontorn, Nattawut Lertkul

# Agenda

1. Q1 Performance Review

2. Q2 Project Roadmap & Priorities

3. Budget Allocation

4. Team Capacity Planning

5. Action Items & Next Steps

## 1. Q1 Performance Review

Tanawat presented the Q1 KPI dashboard. Overall revenue reached 94% of target (฿12.3M vs ฿13.1M goal). Customer satisfaction score improved from 78 to 83 out of 100. Three major product features shipped on time; one (Advanced Analytics module) was delayed by two weeks due to third-party API issues.

Key takeaways:
• On-time delivery rate: 75% (target 80%) — needs improvement
• Support ticket volume down 18% YoY
• Top customer feedback theme: 'faster onboarding experience'

## 2. Q2 Project Roadmap & Priorities

Siriphon walked the team through the Q2 roadmap. Three strategic initiatives were confirmed:

| Project | Priority | Timeline | Owner |
| --- | --- | --- | --- |
| Website Redesign | High | May 1 – June 30, 2026 | Apinya Soontorn |
| Mobile App v2.0 | High | May 15 – July 31, 2026 | Nattawut Lertkul |
| Customer Portal Upgrade | Medium | June 1 – July 15, 2026 | Rattana Promchai |

## 3. Budget Allocation

Total Q2 technology budget: ฿4,200,000. Proposed allocation:

| Project | Budget | % of Total |
| --- | --- | --- |
| Website Redesign | ฿1,500,000 | 36% |
| Mobile App v2.0 | ฿1,800,000 | 43% |
| Customer Portal Upgrade | ฿600,000 | 14% |
| Contingency | ฿300,000 | 7% |

## 4. Team Capacity Planning

Kanokporn noted that two senior engineers will be on leave in June. The team agreed to:

• Front-load critical development tasks before June 10

• Bring in one contract developer for Mobile App UI work (budget approved above)

• Daily stand-up meeting shortened to 10 minutes to protect focus time

## 5. Action Items & Next Steps

| Owner | Action | Due Date |
| --- | --- | --- |
| Apinya Soontorn | Share Website Redesign wireframes with full team | April 22, 2026 |
| Nattawut Lertkul | Finalize Mobile App v2.0 tech stack decision | April 25, 2026 |
| Rattana Promchai | Draft Customer Portal requirements document | April 28, 2026 |
| Kanokporn Wattanasuk | Post contract developer job listing on LinkedIn | April 20, 2026 |
| Tanawat Boonlert | Schedule Q2 kick-off all-hands meeting | April 21, 2026 |

Next meeting: May 2, 2026 – Q2 Kick-off (All-Hands)