## Slide 1
Website Redesign Project
Project Overview & Status Update
Q2 2026 | ACME Corporation | PM: Kanokporn Wattanasuk
Prepared: May 13, 2026

## Slide 2
Project Goals & Scope
🎯 Improve UX & Conversion
Redesign all customer-facing pages with a modern, mobile-first UI. Target: +25% add-to-cart rate.
⚡ Performance
Achieve Core Web Vitals LCP < 2.5 s, CLS < 0.1, FID < 100 ms on all key pages.
♿ Accessibility
Meet WCAG 2.1 Level AA to broaden audience and comply with upcoming regulations.
🔌 CMS Flexibility
Migrate to headless WordPress so the marketing team can publish content without developer help.
📱 Mobile Responsive
Ensure pixel-perfect experience on iOS 17 / Android 14 across 4 key breakpoints.

## Slide 3
Timeline & Key Milestones
#
Dates
Milestone
Status
M1
May 1–12
Discovery & IA
Done
M2
May 13–30
Wireframes & Design System
In Progress
M3
Jun 1–16
High-fidelity UI Design
Not Started
M4
Jun 5–26
Front-end Development
Not Started
M5
Jun 22–28
QA & Accessibility Review
Not Started
M6
Jun 28–30
UAT & Production Deploy
Not Started

## Slide 4
Team & Budget
Team Members
Kanokporn Wattanasuk
Project Manager
Apinya Soontorn
UX / Product Design
Siriphon Chaiyaporn
UI Design
Nattawut Lertkul
Front-end Development
Rattana Promchai
Front-end / CMS
Tanawat Boonlert
QA & Analytics
Budget Summary
Website Redesign
฿1,500,000
36%
Mobile App v2.0
฿1,800,000
43%
Customer Portal Upgrade
฿600,000
14%
Contingency
฿300,000
7%
Total Q2 Tech Budget
฿4,200,000
100%

## Slide 5
Risks, Issues & Next Steps
Current Risks
🔴 HIGH
Team capacity in June
Two senior engineers on leave Jun 10–20. Contract developer hire approved to cover Mobile App UI.
🟡 MEDIUM
Checkout flow design dependency
Payment gateway spec still pending from client. Blocker for T-009, T-012. Escalated to PM.
🟡 MEDIUM
Accessibility WCAG checklist
Client has not delivered WCAG checklist. T-015 blocked. Deadline reminder sent April 22.
🟢 LOW
Scope creep
Client requested blog module addition. Scope change request raised; decision expected May 20.
Immediate Next Steps
▶ Wireframe review & sign-off by May 26 ▶ UI Design System v1.0 release by May 30 ▶ Contract developer on-board by May 20 ▶ Client WCAG checklist deadline: May 21 (escalated) ▶ Q2 mid-point review: June 15, 2026