## Task Tracker
Task ID | Task Name | Assigned To | Status | Priority | Start Date | Due Date | % Complete | Notes
T-001 | Discovery & stakeholder interviews | Apinya Soontorn | Done | High | 2026-05-01 | 2026-05-05 | 100 | 5 stakeholders interviewed
T-002 | Competitive analysis & benchmark report | Tanawat Boonlert | Done | Medium | 2026-05-01 | 2026-05-07 | 100 | Report shared in Teams channel
T-003 | IA & sitemap design | Apinya Soontorn | Done | High | 2026-05-06 | 2026-05-12 | 100 | Approved by stakeholders
T-004 | Wireframes – Desktop (all pages) | Apinya Soontorn | Done | High | 2026-05-08 | 2026-05-16 | 100
T-005 | Wireframes – Mobile responsive | Siriphon Chaiyaporn | In Progress | High | 2026-05-16 | 2026-05-26 | 60 | Homepage & About done
T-006 | UI Design System & Component Library | Siriphon Chaiyaporn | In Progress | High | 2026-05-18 | 2026-05-30 | 40 | Color tokens & typography defined
T-007 | High-fidelity UI design – Homepage | Siriphon Chaiyaporn | In Progress | High | 2026-05-26 | 2026-06-04 | 20
T-008 | High-fidelity UI design – Product pages | Siriphon Chaiyaporn | Not Started | High | 2026-06-02 | 2026-06-12 | 0 | Depends on T-007
T-009 | High-fidelity UI design – Checkout flow | Siriphon Chaiyaporn | Not Started | High | 2026-06-08 | 2026-06-16 | 0 | Requires payment gateway spec
T-010 | Front-end development – Homepage | Nattawut Lertkul | Not Started | High | 2026-06-05 | 2026-06-15 | 0
T-011 | Front-end development – Product pages | Nattawut Lertkul | Not Started | High | 2026-06-13 | 2026-06-22 | 0
T-012 | Front-end development – Checkout flow | Rattana Promchai | Not Started | High | 2026-06-17 | 2026-06-25 | 0
T-013 | CMS integration (WordPress headless) | Rattana Promchai | Not Started | Medium | 2026-06-10 | 2026-06-22 | 0
T-014 | SEO audit & meta-tag implementation | Tanawat Boonlert | Not Started | Medium | 2026-06-20 | 2026-06-26 | 0
T-015 | Accessibility review (WCAG 2.1 AA) | Nattawut Lertkul | Blocked | High | 2026-06-22 | 2026-06-28 | 0 | Awaiting WCAG checklist from client
T-016 | Performance optimization & Core Web Vitals | Rattana Promchai | Not Started | Medium | 2026-06-23 | 2026-06-28 | 0
T-017 | QA testing – functional & regression | Kanokporn Wattanasuk | Not Started | High | 2026-06-25 | 2026-06-29 | 0
T-018 | UAT with client stakeholders | Apinya Soontorn | Not Started | High | 2026-06-28 | 2026-06-30 | 0
T-019 | Production deployment & DNS cutover | Nattawut Lertkul | Not Started | High | 2026-06-30 | 2026-06-30 | 0
T-020 | Post-launch monitoring (48 hrs) | Rattana Promchai | Not Started | Medium | 2026-07-01 | 2026-07-02 | 0

## Project Summary
Website Redesign – Project Summary
Project Name | Website Redesign
Client | ACME Corporation (Internal)
Project Manager | Kanokporn Wattanasuk
Start Date | May 1, 2026
Target Go-Live | June 30, 2026
Status | In Progress
── Task Overview ──
Total Tasks | 20
Done | 4
In Progress | 3
Not Started | 12
Blocked | 1
Overall Completion | 26%
── Risks & Issues ──
Risk 1 | Two senior engineers on leave June 10–20 — mitigation: contract hire approved
Risk 2 | Checkout flow design depends on payment gateway specification (pending client)
Risk 3 | Accessibility review blocked — WCAG checklist still awaited from client (T-015)